## Sheet1
| *Week of June 22nd | Week of June 29nd | Week of July 6th | Week of July 13th | ** Week of July 20th | ** Week of July 27th | Week of August 3rd | Week of August 10th | Week of August 17th | Week of August 24th | Week of August 30th
Jobs | * | Complete the data model | Implementing CRUD | Switching to PostgreSQL | Integration | User Interface | Testing | Feature enhancement | Deployment
Students | * | Complete the data model | Implementing CRUD | Switching to PostgreSQL | Integration | User Interface | Testing
Billing | * | Complete the data model | Implementing CRUD | Switching to PostgreSQL | Integration | User Interface | Testing
Schedules | * | Complete the data model | Implementing CRUD | Switching to PostgreSQL | Integration | User Interface | Testing
Time Sheets | * | Complete the data model | Implementing CRUD | Switching to PostgreSQL | Integration | User Interface | Testing
Calender | * | Complete the data model | Implementing CRUD | Switching to PostgreSQL | Integration | User Interface | Testing
WIA/WDP | * | Complete the data model | Implementing CRUD | Switching to PostgreSQL | Integration | User Interface | Testing
Administration | * | Complete the data model | Implementing CRUD | Switching to PostgreSQL | Integration | User Interface | Testing
* Jack will break the data model between the applications and assign them to each team members. This will be done before June 22nd
** We will have to break up the team and assignment based on the need.